{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":1,"comments":1,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":40,"n_cols":13,"rows_kept":40,"cut":false,"hidden":false,"merged":[[1,1,7,1],[8,1,12,1],[14,1,21,1],[22,1,27,1],[28,1,34,1],[35,1,38,1]]}
["序号","功能模块","需求","操作页面","备注","优先级","开发人员","计划开始日期","计划完成日期","开始测试时间","最新测试结果","描述","备注"]
[1,"基础维护","工厂维护",null,null,"高","杨智伟","2022-09-12","2022-09-14"]
[2,null,"车间维护",null,null,"高","杨智伟","2022-09-12","2022-09-14"]
[3,null,"产线维护",null,null,"高","杨智伟","2022-09-12","2022-09-14"]
[4,null,"设备档案维护",null,null,"高","杨智伟","2022-09-12","2022-09-14"]
[5,null,"标签模板维护",null,null,"高","杨智伟","2022-09-12","2022-09-14"]
[6,null,"产品BOM维护",null,"1.注意界面UI，参考方案内容；（逻辑功能和要求）  \n2.先做导入，删除功能","高","杨智伟","2022-09-15","2022-09-17"]
[7,null,"物料档案维护",null,"同步K3非研发物料","高","杨智伟","2022-09-15","2022-09-17"]
[8,"工艺管理","工序维护",null,null,"高","杨智伟","2022-09-19","2022-09-22"]
[9,null,"工艺路线维护",null,"1.注意界面UI，参考方案内容；（逻辑功能和要求）  ","高","杨智伟","2022-09-19","2022-09-22"]
[10,null,"产品-工艺路线绑定",null,"1.注意界面UI，参考方案内容；（逻辑功能和要求）  ","高","杨智伟","2022-09-19","2022-09-22"]
[11,null,"标准工时维护",null,"1.注意界面UI，参考方案内容；（逻辑功能和要求）  ","中","杨智伟","2022-09-30","2022-09-30"]
[12,null,"产品工序绑定子件",null,"参考智绿  ","高","杨智伟","2022-09-19","2022-09-22"]
[13,"仓库管理","线边仓条码打印",null,"1.注意界面UI，参考方案内容；（逻辑功能和要求）  \n2.参考鑫宏涛条码生成","中","韩付","2022-09-26","2022-09-30"]
[14,"生产管理","工单管理",null,"1.注意界面UI，参考方案内容；（逻辑功能和要求）  \n2.异常状态数据库实为暂停，涉及附件上传功能，都为上传1个；","高","韩付","2022-09-12","2022-09-16"]
[15,null,"线边仓管理",null,"1.注意界面UI，参考方案内容；（逻辑功能和要求）  ","高","韩付","2022-09-12","2022-09-16"]
[16,null,"人员技能矩阵",null,"1.注意界面UI，参考方案内容；（逻辑功能和要求）  ","高","韩付","2022-09-12","2022-09-16"]
[17,null,"生产报工",null,"1.注意界面UI，参考方案内容；（逻辑功能和要求）  \n2.上料参考自控","高","韩付","2022-09-17","2022-09-24"]
[18,null,"盘条码生成",null,"1.注意界面UI，参考方案内容；（逻辑功能和要求）  ","中","韩付","2022-09-26","2022-09-30"]
[19,null,"盘条码绑定",null,"1.注意界面UI，参考方案内容；（逻辑功能和要求）  ","中","韩付","2022-09-26","2022-09-30"]
[20,null,"箱号生成",null,null,"中","韩付","2022-09-26","2022-09-30"]
[21,null,"装箱",null,"1.注意界面UI，参考方案内容；（逻辑功能和要求）  \n2.参考聚天合","中","韩付","2022-09-26","2022-09-30"]
[22,"质量管理","不良代码维护",null,null,"高","杨智伟","2022-09-23","2022-09-29"]
[23,null,"检验项目维护",null,null,"高","杨智伟","2022-09-23","2022-09-29"]
[24,null,"检验项目关联",null,"物料+工序的维度","高","杨智伟","2022-09-23","2022-09-29"]
[25,null,"IPQC检验",null,"1.注意界面UI，参考方案内容；（逻辑功能和要求） ","高","杨智伟","2022-09-23","2022-09-29"]
[26,null,"品质终判",null,null,"高","杨智伟","2022-09-23","2022-09-29"]
[27,null,"客诉信息反馈",null,null,"中","杨智伟","2022-10-10","2022-10-12"]
[28,"追溯查询","项目进度查询",null,null,"中","韩付","2022-10-10","2022-10-21"]
[29,null,"报工不良查询",null,null,"中","杨智伟","2022-10-13","2022-10-21"]
[30,null,"工序流转时间及预警汇总表",null,null,"中","韩付","2022-10-10","2022-10-21"]
[31,null,"生产日报表",null,null,"中","韩付","2022-10-10","2022-10-21"]
[32,null,"生产良率统计",null,null,"中","韩付","2022-10-10","2022-10-21"]
[33,null,"生产计划达成率",null,null,"中","韩付","2022-10-10","2022-10-21"]
[34,null,"工单执行进度汇总",null,null,"中","杨智伟","2022-10-13","2022-10-21"]
[35,"看板管理","冷压车间看板",null,null,"中","杨智伟","2022-10-13","2022-10-21"]
[36,null,"绕线车间看板",null,null,"中","杨智伟","2022-10-13","2022-10-21"]
[37,null,"热压车间看板",null,null,"中","杨智伟","2022-10-13","2022-10-21"]
[38,null,"车间综合看板",null,null,"中","杨智伟","2022-10-13","2022-10-21"]
[null,"采集同步","采集",null,null,"中","韩付","2022-10-10","2022-10-21"]